## Chapter
Goa Chapter
Chapter settings
id | goa
name | Goa Chapter
accent | amber
timeZone | Asia/Kolkata
timeZoneLabel | Goa, India
CRM Collection year | 2026
How to use this workbook
Blue cells | Type in these. Everything you maintain is blue.
Black cells | Formulas. Do not overwrite - they recalculate.
Grey id column | The join key. Never edit or reorder it.
CRM Collection maps to Live Projects through it.
Formats
Money | Whole rupees, e.g. 240000000. The dashboard shows ₹24Cr.
Percentage of completion | A number from 0 to 100, e.g. 82. Not 0.82.
Expected handover / Onward | Free text, e.g. Mar 2026 or Q3 2027.
Handover value Delivered | Spelled exactly, it shows as a green pill.
Status | Land acquired / Approvals in progress / Design stage /
Yard slot booked. Anything else works, it just shows grey.
Empty CRM month | Leave blank. The dashboard shows a dash.
Rows | Row 2 down are real examples - overwrite them or add below.
Adding a project | Add the row in Live Projects, then add its column
in CRM Collection with the same project name.
Allocated amount + extra | Calculated as Amount opex plus Extra (column B + C).
Source of the seed values | Placeholder figures supplied by the dashboard build,
not real accounts. Replace them all.

## Live Projects
Live projects | Percentage of completion (Lindsay) | Total sold assets (CRM) | Inventory (Lincoln) | Expected outcome (Lindsay) | Expected handover (Lindsay) | Amount repaid to first project (Lindsay) | Year started (CRM) | Comments (Lincoln) | id (do not edit)
Project One | 100 | 24 | 0 | 180000000 | Delivered | 0 | 2019 | Fully handed over, closing formalities done. | goa-p1
Project Two | 82 | 18 | 6 | 240000000 | Mar 2026 | 45000000 | 2021 | Finishing works on track; 6 units still open. | goa-p2
Project Three | 54 | 11 | 14 | 310000000 | Dec 2026 | 20000000 | 2023 | Structure complete, MEP in progress. | goa-p3
Project Four | 18 | 4 | 22 | 400000000 | Q3 2027 | 0 | 2025 | Foundation stage; launch pricing under review. | goa-p4

## Pipeline
Pipeline project | Onward (Lincoln) | Inventory (Lincoln/Lindsay) | Ticket size (Lincoln) | Total cost of construction (Lincoln/Lindsay) | Planned (Lincoln) | Status (Lincoln) | id (do not edit)
Pipeline One | Apr 2026 | 30 | 25000000 | 450000000 | 30 | Land acquired | goa-pl1
Pipeline Two | Oct 2026 | 18 | 32000000 | 380000000 | 18 | Approvals in progress | goa-pl2
Pipeline Three | Q2 2027 | 42 | 18000000 | 520000000 | 48 | Design stage | goa-pl3

## Opex
Opex | Amount opex (Lincoln) | Extra (Lincoln) | Remark (Lincoln) | Allocated amount + extra | id (do not edit)
Site office | 1200000 | 150000 | Lease renewed for the year. | 1350000 | goa-o1
Marketing | 3500000 | 400000 | Extra spend on the launch campaign. | 3900000 | goa-o2
Salaries | 8400000 | 0 |  | 8400000 | goa-o3
Maintenance | 950000 | 75000 | AMC revised in April. | 1025000 | goa-o4

## CRM Collection
Month (Lendl) | Project One | Project Two | Project Three | Project Four
Jan | 2000000 | 7200000 | 3400000
Feb | 1500000 | 6800000 | 4100000
Mar | 600000 | 8100000 | 3900000
Apr |  | 5400000 | 5200000 | 1200000
May |  | 7900000 | 4600000 | 2400000
Jun |  | 6200000 | 5800000 | 1900000
Jul |  | 8600000 | 4300000 | 3100000
Aug |  | 7100000 | 6000000 | 2700000
Sep
Oct
Nov
Dec
Total | 4100000 | 57300000 | 37300000 | 11300000