## Chapter
Portugal Chapter
Chapter settings
id | portugal
name | Portugal Chapter
accent | indigo
timeZone | Europe/Lisbon
timeZoneLabel | Portugal
CRM Collection year | 2026
How to use this workbook
Blue cells | Type in these. Everything you maintain is blue.
Black cells | Formulas. Do not overwrite - they recalculate.
Grey id column | The join key. Never edit or reorder it.
CRM Collection maps to Live Projects through it.
Formats
Money | Whole rupees, e.g. 240000000. The dashboard shows ₹24Cr.
Percentage of completion | A number from 0 to 100, e.g. 82. Not 0.82.
Expected handover / Onward | Free text, e.g. Mar 2026 or Q3 2027.
Handover value Delivered | Spelled exactly, it shows as a green pill.
Status | Land acquired / Approvals in progress / Design stage /
Yard slot booked. Anything else works, it just shows grey.
Empty CRM month | Leave blank. The dashboard shows a dash.
Rows | Row 2 down are real examples - overwrite them or add below.
Adding a project | Add the row in Live Projects, then add its column
in CRM Collection with the same project name.
Allocated amount + extra | Calculated as Amount opex plus Extra (column B + C).
Source of the seed values | Placeholder figures supplied by the dashboard build,
not real accounts. Replace them all.

## Live Projects
Live projects | Percentage of completion (Lindsay) | Total sold assets (CRM) | Inventory (Lincoln) | Expected outcome (Lindsay) | Expected handover (Lindsay) | Amount repaid to first project (Lindsay) | Year started (CRM) | Comments (Lincoln) | id (do not edit)
Project One | 91 | 14 | 2 | 120000000 | Jan 2026 | 30000000 | 2022 | Snagging under way, handover set for January. | pt-p1
Project Two | 47 | 9 | 12 | 210000000 | Nov 2026 | 15000000 | 2024 | Facade works started; sales pace steady. | pt-p2
Project Three | 12 | 3 | 19 | 260000000 | Q4 2027 | 0 | 2025 | Excavation stage. | pt-p3

## Pipeline
Pipeline project | Onward (Lincoln) | Inventory (Lincoln/Lindsay) | Ticket size (Lincoln) | Total cost of construction (Lincoln/Lindsay) | Planned (Lincoln) | Status (Lincoln) | id (do not edit)
Pipeline One | Jun 2026 | 22 | 28000000 | 300000000 | 22 | Land acquired | pt-pl1
Pipeline Two | Q1 2027 | 16 | 35000000 | 340000000 | 20 | Approvals in progress | pt-pl2

## Opex
Opex | Amount opex (Lincoln) | Extra (Lincoln) | Remark (Lincoln) | Allocated amount + extra | id (do not edit)
Site office | 800000 | 90000 | Shared with Project Two. | 890000 | pt-o1
Marketing | 2100000 | 260000 | Portal listings added. | 2360000 | pt-o2
Salaries | 5600000 | 0 |  | 5600000 | pt-o3
Maintenance | 620000 | 40000 | Landscaping contract. | 660000 | pt-o4

## CRM Collection
Month (Lendl) | Project One | Project Two | Project Three
Jan | 4800000 | 3100000
Feb | 5200000 | 2800000
Mar | 4100000 | 3700000
Apr | 3600000 | 4200000
May | 2900000 | 3900000
Jun | 2200000 | 4500000 | 900000
Jul |  | 3300000 | 1600000
Aug |  | 4800000 | 2100000
Sep
Oct
Nov
Dec
Total | 22800000 | 30300000 | 4600000